## Instructions
Leadership Sync — data template
This workbook is the offline way to add or edit the tracker data.
Each tab is one collection in the dashboard. Fill in the rows, then
import the file in the web app (sidebar → Import Excel).
How to use
1. Edit the Customers, Projects, Milestones and Decisions tabs.
2. One row = one record. Keep the header row unchanged.
3. Leave the 'id' cell BLANK for a new record — one is generated on import.
Keep the existing 'id' to update that same record.
4. 'status' accepts: Not started, Green, Amber, Red, Done.
5. Dates use ISO format YYYY-MM-DD (e.g. 2026-09-30).
6. milestones.projectId must match a projects.id value.
7. 'updatedAt' can be left blank — the app stamps it on import.
Notes
• Importing UPSERTS: rows with an existing id overwrite that record;
rows without an id are added. It does not delete other records.
• The data currently in the tracker is pre-filled here as a starting point.

## Customers
id | code | name | site | useCase | phase | stage | status | statusReason | csLead | techOwner | salesOwner | nextMilestone | targetDate | blocker | decisionNeeded | notes | updatedAt
A-01 | A-01 | Forvia (Faurecia Seating) | Auburn Hills, MI | Weld-defect inspection, Tesla Opal seat frames (60% / 40%) | Pilot | A1 Scoping | Amber | CAD needed to confirm camera count | Nitin | Ravi | Nitin | Milestone 1 scope (defects / SKU / stations) agreed |  | CAD for camera count; capture ownership (Insight vs. Dori); business case / capital approval | TRUE | Details as of Jul 2026; update at first review | 2026-09-18T12:00:00Z
A-02 | A-02 | Magna Casting North America | Birmingham, AL (Kamtek) | Die-cast aluminum part inspection (rear rails, shock towers) | Pilot | A1 Scoping | Amber | defect priorities not yet set | Nitin | Ravi | Nitin | Milestone 1 line / SKU and 1–2 defects selected |  | Defect priority set; station-to-defect mapping; sample images and parts; core-pin depth feasibility | TRUE | Details as of Jul 2026; update at first review | 2026-09-18T12:00:00Z

## Projects
id | code | name | track | objective | responsible | team | updatedAt
B-01 | B-01 | Anomaly detection workflow | B | Make anomaly detection a repeatable, config-driven platform workflow. | Ravi |  | 2026-09-18T12:00:00Z
B-02 | B-02 | VLM R&D and quick pilots | B | Find where vision-language models beat or complement the current CV stack; adopt, watch or park. | Ravi |  | 2026-09-18T12:00:00Z
B-03 | B-03 | Document AI | B | Reusable document intelligence: extract, validate and cross-check manufacturing documents. | Ravi |  | 2026-09-18T12:00:00Z
C-01 | C-01 | Falcon | C | Rebuild the platform with Claude: event-driven, config-driven, headless, API-first, fully documented. | Ravi |  | 2026-09-18T12:00:00Z
C-02 | C-02 | Pallet Scan | C | Productized Pallet Scan: 5-app suite on Design System v1 with the six-model edge pipeline. | Ravi |  | 2026-09-18T12:00:00Z
C-03 | C-03 | Document Management | C | Customer-facing app on Document AI: intake, review, audit trail, reporting. | Ravi |  | 2026-09-18T12:00:00Z
C-04 | C-04 | Application Builder | C | UX-driven builder on Falcon to assemble applications from building blocks without code. | Ravi |  | 2026-09-18T12:00:00Z
C-05 | C-05 | Quality Inspection | C | Inline and offline visual defect detection. | Ravi |  | 2026-09-18T12:00:00Z
C-06 | C-06 | SOP Verification | C | Verify operators follow each work-instruction step, in order. | Ravi |  | 2026-09-18T12:00:00Z
C-07 | C-07 | Kitting Verification | C | Confirm every kit has the right parts and quantities. | Ravi |  | 2026-09-18T12:00:00Z
C-08 | C-08 | Safety & EHS | C | Detect unsafe conditions and behaviors and alert in real time. | Ravi |  | 2026-09-18T12:00:00Z
C-09 | C-09 | Productivity Monitoring | C | Measure cycle times, utilization and bottlenecks. | Ravi |  | 2026-09-18T12:00:00Z
D-01 | D-01 | Camera, lens & lighting standards + tool | D | Standard camera, lens and lighting configurations plus a CS selection tool. | Ravi |  | 2026-09-18T12:00:00Z
D-02 | D-02 | Edge server standards + tool | D | Standard edge server configurations plus a CS selection tool. | Ravi |  | 2026-09-18T12:00:00Z
D-03 | D-03 | Data Collector & Configurator | D | Customer-facing tool to pass requirements, site details and sample data to Dori. | Nitin |  | 2026-09-18T12:00:00Z
D-04 | D-04 | Cost & infrastructure monitoring | D | Live cost and infrastructure visibility by customer, application and R&D. | Ravi |  | 2026-09-18T12:00:00Z

## Milestones
id | projectId | seq | name | deliverable | owner | status | targetDate | doneDate | blocker | decisionNeeded | notes | updatedAt
B-01-M1 | B-01 | 1 | M1 Spec + current-state review | Workflow spec |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-01-M2 | B-01 | 2 | M2 End-to-end pipeline on 1 dataset | Automated train / eval pipeline |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-01-M3 | B-01 | 3 | M3 Benchmark on 3 datasets + calibration | Benchmark test report, model card |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-01-M4 | B-01 | 4 | M4 Edge deployment | SE / CS runbook |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-01-M5 | B-01 | 5 | M5 Released as platform workflow | Setup screen, CS training |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-02-M1 | B-02 | 1 | M1 Shortlist + pilot selection | Evaluation protocol |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-02-M2 | B-02 | 2 | M2 Pilot 1 | Pilot results report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-02-M3 | B-02 | 3 | M3 Pilots 2–3 | Pilot results reports, demo |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-02-M4 | B-02 | 4 | M4 Recommendation | Adopt / watch / park memo |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-03-M1 | B-03 | 1 | M1 Document taxonomy + schemas | Capability spec |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-03-M2 | B-03 | 2 | M2 Extraction baseline (DHR) | Baseline accuracy results |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-03-M3 | B-03 | 3 | M3 Validation rules + drawing baseline | Pipeline, accuracy report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-03-M4 | B-03 | 4 | M4 Human-in-the-loop review | Review screen (wireframe, then build) |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
B-03-M5 | B-03 | 5 | M5 Packaged as platform workflow | API docs, release |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M1 | C-01 | 1 | M1 Target architecture | Architecture doc, Claude engineering standards |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M2 | C-01 | 2 | M2 API design | API spec, docs site |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M3 | C-01 | 3 | M3 Core services | Services, integration test reports |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M4 | C-01 | 4 | M4 Configuration UX | Config screens, user guide |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M5 | C-01 | 5 | M5 Monitoring & tools UX | System Health, logs, alerts, admin tools |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M6 | C-01 | 6 | M6 Migration plan + pilot migration | Migration runbook, first customer moved |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-01-M7 | C-01 | 7 | M7 General release | Release notes, full documentation |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-02-M1 | C-02 | 1 | M1 Spec lock | Product spec, final UX designs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-02-M2 | C-02 | 2 | M2 Edge pipeline hardened | Model cards, performance report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-02-M3 | C-02 | 3 | M3 Apps build (1) | Operator + Operations apps |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-02-M4 | C-02 | 4 | M4 Apps build (2) | Business, Sites, System Health apps |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-02-M5 | C-02 | 5 | M5 Validation | End-to-end test report (lab + site) |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-02-M6 | C-02 | 6 | M6 Release | Runbook, user guides, demo environment |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-03-M1 | C-03 | 1 | M1 Product spec + UX | Spec, workflow maps, UX designs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-03-M2 | C-03 | 2 | M2 Core app build | Intake, review, exception screens |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-03-M3 | C-03 | 3 | M3 Integration with B-03 | Integration test report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-03-M4 | C-03 | 4 | M4 Audit & compliance | Audit trail, e-signature, checklist |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-03-M5 | C-03 | 5 | M5 Release | User guide, runbook, demo environment |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-04-M1 | C-04 | 1 | M1 Concept + UX | Builder spec, UX prototype |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-04-M2 | C-04 | 2 | M2 Building-block framework | Component SDK, docs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-04-M3 | C-04 | 3 | M3 Builder MVP | Workflow composer + template library |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-04-M4 | C-04 | 4 | M4 Internal pilot | One existing app rebuilt; test report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-04-M5 | C-04 | 5 | M5 Release to SEs | Builder guide, training |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-05-M1 | C-05 | 1 | M1 Current-state audit | Audit report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-05-M2 | C-05 | 2 | M2 Enhancement backlog | Prioritized roadmap |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-05-M3 | C-05 | 3 | M3 Documentation current | Spec, user guide, runbook, API docs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-05-M4 | C-05 | 4 | M4 UX refresh | Screens on Design System v1 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-05-M5 | C-05 | 5 | M5 Migration to Falcon | Migration plan, test report, cutover |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-05-M6 | C-05 | 6 | M6 Application Builder template | Template + validation report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-06-M1 | C-06 | 1 | M1 Current-state audit | Audit report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-06-M2 | C-06 | 2 | M2 Enhancement backlog | Prioritized roadmap |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-06-M3 | C-06 | 3 | M3 Documentation current | Spec, user guide, runbook, API docs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-06-M4 | C-06 | 4 | M4 UX refresh | Screens on Design System v1 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-06-M5 | C-06 | 5 | M5 Migration to Falcon | Migration plan, test report, cutover |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-06-M6 | C-06 | 6 | M6 Application Builder template | Template + validation report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-07-M1 | C-07 | 1 | M1 Current-state audit | Audit report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-07-M2 | C-07 | 2 | M2 Enhancement backlog | Prioritized roadmap |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-07-M3 | C-07 | 3 | M3 Documentation current | Spec, user guide, runbook, API docs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-07-M4 | C-07 | 4 | M4 UX refresh | Screens on Design System v1 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-07-M5 | C-07 | 5 | M5 Migration to Falcon | Migration plan, test report, cutover |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-07-M6 | C-07 | 6 | M6 Application Builder template | Template + validation report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-08-M1 | C-08 | 1 | M1 Current-state audit | Audit report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-08-M2 | C-08 | 2 | M2 Enhancement backlog | Prioritized roadmap |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-08-M3 | C-08 | 3 | M3 Documentation current | Spec, user guide, runbook, API docs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-08-M4 | C-08 | 4 | M4 UX refresh | Screens on Design System v1 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-08-M5 | C-08 | 5 | M5 Migration to Falcon | Migration plan, test report, cutover |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-08-M6 | C-08 | 6 | M6 Application Builder template | Template + validation report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-09-M1 | C-09 | 1 | M1 Current-state audit | Audit report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-09-M2 | C-09 | 2 | M2 Enhancement backlog | Prioritized roadmap |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-09-M3 | C-09 | 3 | M3 Documentation current | Spec, user guide, runbook, API docs |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-09-M4 | C-09 | 4 | M4 UX refresh | Screens on Design System v1 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-09-M5 | C-09 | 5 | M5 Migration to Falcon | Migration plan, test report, cutover |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
C-09-M6 | C-09 | 6 | M6 Application Builder template | Template + validation report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-01-M1 | D-01 | 1 | M1 Selection logic + reference matrix | Matrix, approved part list |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-01-M2 | D-01 | 2 | M2 Lab validation | Validation report per configuration |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-01-M3 | D-01 | 3 | M3 Publish | PPT + Word guide |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-01-M4 | D-01 | 4 | M4 CS tool build | Internal tool (builds on vision calculator) |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-01-M5 | D-01 | 5 | M5 Trial with CS + training | Final tool, trained CS |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-02-M1 | D-02 | 1 | M1 Reference configurations | S / M / L configuration sheet |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-02-M2 | D-02 | 2 | M2 Benchmarking | Throughput benchmark report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-02-M3 | D-02 | 3 | M3 Publish | PPT + Word guide (incl. IT & security) |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-02-M4 | D-02 | 4 | M4 CS tool build | Internal tool, shared intake with D-01 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-02-M5 | D-02 | 5 | M5 Trial with CS + training | Final tool, trained CS |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-03-M1 | D-03 | 1 | M1 Requirements schemas | Schema doc per application |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-03-M2 | D-03 | 2 | M2 UX design | Designs on Design System v1 |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-03-M3 | D-03 | 3 | M3 V1 for first 2 apps | Working app |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-03-M4 | D-03 | 4 | M4 Pilot with 2 customers | Pilot report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-03-M5 | D-03 | 5 | M5 V1 for remaining apps | Working apps |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-03-M6 | D-03 | 6 | M6 Release | User guide, video, CS playbook |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-04-M1 | D-04 | 1 | M1 Tagging standard + data sources | Standard doc, source inventory |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-04-M2 | D-04 | 2 | M2 Data pipeline | Working ingestion |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-04-M3 | D-04 | 3 | M3 Dashboard V1 | Live web tool |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-04-M4 | D-04 | 4 | M4 Alerts + optimization | Alert rules, first optimization report |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z
D-04-M5 | D-04 | 5 | M5 Cost-to-serve per customer | Customer cost report (feeds pricing) |  | Not started |  |  |  | FALSE |  | 2026-09-18T12:00:00Z

## Decisions
id | n | type | item | ref | owner | meeting | date | due | status | outcome | updatedAt
d001 | 1 | Decision | Confirm days and times for the three weekly sessions | All | Vivek | Mon engineering | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z
d002 | 2 | Decision | Document AI: internal R&D or product line from day one? | B-03 | Ravi | Mon engineering | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z
d003 | 3 | Decision | Pallet Scan and Document Management: ship on the current platform or on Falcon? | C-02 / C-03 | Ravi | Mon engineering | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z
d004 | 4 | Decision | Migration order for existing applications | C-05 to C-09 | Ravi | Mon engineering | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z
d005 | 5 | Decision | D-04: standalone now or part of Falcon? | D-04 | Ravi | Mon engineering | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z
d006 | 6 | Action | Name teams and set milestone dates on all engineering projects | B / C / D | Ravi | Mon engineering | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z
d007 | 7 | Action | Load the full Track A customer list | Track A | Nitin | Wed customer & CS | 2026-09-18 |  | Open |  | 2026-09-18T12:00:00Z